## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a new user, I want to sign up using my email or mobile number so that I can create an account securely. | 5
US-2 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a returning user, I want to log in using my email or phone and password so that I can access my account easily. | 5
US-3 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want an option to recover my password via a 'Forgot Password' process so that I can regain access if I forget my password. | 8
US-4 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want basic security validations on my input fields so that my data is protected from common risks. | 8
US-5 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a visitor, I want to see a prominent 'Create an account' section so that I am encouraged to register. | 2
US-6 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a visitor, I want to see clear call-to-action buttons during onboarding so that I am guided through steps easily. | 3
US-7 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a visitor, I want to see the Facebook logo and tagline so that I recognize the branding clearly. | 1
US-8 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a user, I want to select my preferred language from supported options at the bottom of the page so that I can navigate in my language. | 5
US-9 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a business owner, I want a link to 'Create Page for a celebrity, brand or business' so I can easily create a page for my entity. | 3
US-10 | Sprint 2 (2025-12-08 – 2025-12-21) | Accessibility & Performance | As a user with accessibility needs, I want the page to comply with WCAG 2.1 standards including alt text and tab navigation so that I can use the site effectively. | 13
US-11 | Sprint 3 (2025-12-22 – 2025-12-31) | Accessibility & Performance | As a visitor, I want the page to be responsive on desktop, tablet, and mobile so that I have a consistent experience across devices. | 8
US-12 | Sprint 3 (2025-12-22 – 2025-12-31) | Accessibility & Performance | As a visitor, I want the landing page to load in under 2 seconds so that I have a fast and smooth browsing experience. | 13