## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a new user, I want to sign up using email or mobile number so that I can create an account securely. | 5
US-2 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a returning user, I want to log in with my email or phone and password so that I can access my account. | 3
US-3 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user who forgot my password, I want to use a recovery process so that I can reset it securely. | 8
US-4 | Sprint 1 (2025-11-24 – 2025-12-07) | Landing Page Content & Branding | As a visitor, I want to see the Facebook branding, logo, and tagline so that I recognize the brand immediately. | 2
US-5 | Sprint 1 (2025-11-24 – 2025-12-07) | Landing Page Content & Branding | As a user, I want to find a prominent 'Create an account' section so that I can easily start signing up. | 2
US-6 | Sprint 2 (2025-12-08 – 2025-12-21) | User Engagement & Onboarding | As a new user, I want clear CTA buttons so that I can understand the next steps easily. | 2
US-7 | Sprint 2 (2025-12-08 – 2025-12-21) | User Engagement & Onboarding | As a visitor, I want a link to 'Create Page for a celebrity, brand or business' so that I can explore business page creation. | 3
US-8 | Sprint 2 (2025-12-08 – 2025-12-21) | Localization & Accessibility | As a user, I want to choose from predefined supported languages so that I can view the page in my preferred language. | 3
US-9 | Sprint 2 (2025-12-08 – 2025-12-21) | Localization & Accessibility | As a user with accessibility needs, I want alt text, labels, and tab navigation so that I can use the page according to WCAG 2.1 standards. | 8
US-10 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a user, I want the language selection at the bottom of the page so that it is easy to find. | 1
US-11 | Sprint 2 (2025-12-08 – 2025-12-21) | Performance & Security | As a user, I want the landing page to load in under 2 seconds so that I have a fast experience. | 13
US-12 | Sprint 3 (2025-12-22 – 2025-12-31) | Performance & Security | As a user, I want input validation on sign-up and login fields so that my data is secure from breaches and errors. | 8