## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want to sign up using my email or mobile number so that I can create an account securely. | 5
US-2 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want to log in with my email or phone and password so that I can access my account. | 5
US-3 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want to use a 'Forgot Password' option so that I can recover my account if I forget my password. | 3
US-4 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a marketing team member, I want the sign-up and login process to have basic security input validations so that user data breaches are minimized. | 8
US-5 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a user, I want to see a prominent 'Create an account' section so that I am encouraged to sign up. | 2
US-6 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a user, I want to see Facebook branding elements including logo and tagline so that I recognize the brand. | 1
US-7 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a user, I want a link to 'Create Page for a celebrity, brand or business' so that I can explore creating specialized pages. | 2
US-8 | Sprint 2 (2025-12-08 – 2025-12-21) | UI/UX & Accessibility | As a user, I want clear CTA buttons for onboarding so that I can easily understand what actions to take. | 3
US-9 | Sprint 2 (2025-12-08 – 2025-12-21) | UI/UX & Accessibility | As a user, I want to select my preferred language from predefined options so that I can use the page in my language. | 3
US-10 | Sprint 2 (2025-12-08 – 2025-12-21) | UI/UX & Accessibility | As a user with disabilities, I want the landing page to comply with WCAG 2.1 accessibility standards so that I can navigate and interact easily using assistive technologies. | 13
US-11 | Sprint 3 (2025-12-22 – 2025-12-31) | UI/UX & Accessibility | As a user, I want the landing page to be responsive on desktop, tablet, and mobile devices so that I have a good experience on any device. | 8
US-12 | Sprint 3 (2025-12-22 – 2025-12-31) | Performance & Security | As a user, I want the landing page to load in under 2 seconds so that I have a fast and smooth experience. | 8