## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want to sign up using email or mobile number so that I can create an account securely. | 8
US-2 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want to log in with my email or phone and password so that I can access my account. | 5
US-3 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want to recover my password via a 'Forgot Password' option so that I can regain access if I forget it. | 5
US-4 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want input fields to have basic security checks so that my data is validated and secure. | 3
US-5 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a visitor, I want to see Facebook branding, logo, and tagline so that I recognize the platform. | 2
US-6 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a visitor, I want a clearly visible 'Create an account' section so that I can easily start signing up. | 2
US-7 | Sprint 2 (2025-12-08 – 2025-12-21) | Landing Page Content & Branding | As a visitor, I want to see a link for 'Create Page for a celebrity, brand or business' so that I can create relevant pages. | 3
US-8 | Sprint 2 (2025-12-08 – 2025-12-21) | User Onboarding & Engagement | As a new user, I want clear CTA buttons during onboarding so that I can proceed without confusion. | 3
US-9 | Sprint 2 (2025-12-08 – 2025-12-21) | User Onboarding & Engagement | As a user, I want to select my preferred language at the bottom of the page so that the content is understandable to me. | 3
US-10 | Sprint 2 (2025-12-08 – 2025-12-21) | Responsive Design & Accessibility | As a user, I want the landing page to be responsive on desktop, tablet, and mobile so that I can use it on any device. | 13
US-11 | Sprint 3 (2025-12-22 – 2025-12-31) | Responsive Design & Accessibility | As a user with disabilities, I want the page to comply with accessibility standards (alt text, labels, tab navigation) so that I can navigate it easily. | 8
US-12 | Sprint 3 (2025-12-22 – 2025-12-31) | Responsive Design & Accessibility | As a user, I want the page to load fast (under 2 seconds) so that I have a smooth experience. | 8