## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want to sign up using my email or mobile number so that I can create a new account easily. | 5
US-2 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want to log in with my email or phone and password so that I can securely access my account. | 5
US-3 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want to use the 'Forgot Password' option so that I can recover my account if I forget my password. | 3
US-4 | Sprint 1 (2025-11-24 – 2025-12-07) | User Authentication & Access | As a user, I want clear and visible 'Create an account' and login sections on the landing page so I can quickly start or access my account. | 3
US-5 | Sprint 1 (2025-11-24 – 2025-12-07) | Landing Page Content & Branding | As a marketing user, I want the landing page to display Facebook branding, logo, and tagline to maintain brand consistency. | 2
US-6 | Sprint 1 (2025-11-24 – 2025-12-07) | Landing Page Content & Branding | As a user, I want to see a link to 'Create Page for a celebrity, brand or business' so that I can navigate to create business-related pages easily. | 2
US-7 | Sprint 1 (2025-11-24 – 2025-12-07) | Landing Page Content & Branding | As a user, I want clear CTA buttons during onboarding so that I am guided to engage with the platform effectively. | 3
US-8 | Sprint 2 (2025-12-08 – 2025-12-21) | User Interface & Accessibility | As a user, I want the landing page to be responsive on desktop, tablet, and mobile so I can access it using any device. | 8
US-9 | Sprint 2 (2025-12-08 – 2025-12-21) | User Interface & Accessibility | As a user with disabilities, I want the page to comply with WCAG 2.1 accessibility standards including alt text, labels, and tab navigation so that I can navigate it easily. | 13
US-10 | Sprint 3 (2025-12-22 – 2025-12-31) | User Interface & Accessibility | As an international user, I want to select my language from a predefined list at the bottom of the page so that I can use the landing page in my preferred language. | 3
US-11 | Sprint 3 (2025-12-22 – 2025-12-31) | Performance & Security | As a user, I want the landing page to load in under 2 seconds so that I have a fast and smooth experience. | 8
US-12 | Sprint 3 (2025-12-22 – 2025-12-31) | Performance & Security | As a system, I want to perform basic security checks on user inputs during sign-up and login so that data breaches and risks are minimized. | 8