## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-12-01 – 2025-12-14) | User Registration & Login | As a user, I want to sign up using my email so that I can create a new account easily. | 3
US-2 | Sprint 1 (2025-12-01 – 2025-12-14) | User Registration & Login | As a user, I want to sign up using my mobile number so that I can register with whichever contact I prefer. | 3
US-3 | Sprint 1 (2025-12-01 – 2025-12-14) | User Registration & Login | As a user, I want to see a prominent 'Create an account' section so that I can quickly start the registration process. | 2
US-4 | Sprint 1 (2025-12-01 – 2025-12-14) | User Registration & Login | As a user, I want a login section with Email/Phone and Password fields so that I can access my existing account. | 5
US-5 | Sprint 1 (2025-12-01 – 2025-12-14) | User Registration & Login | As a user, I want a 'Forgot Password' recovery option so that I can reset my password if I forget it. | 5
US-6 | Sprint 1 (2025-12-01 – 2025-12-14) | User Onboarding & Call to Action | As a new user, I want clear CTA buttons during onboarding so that I can easily understand the next steps. | 2
US-7 | Sprint 1 (2025-12-01 – 2025-12-14) | User Onboarding & Call to Action | As a user, I want a link to 'Create Page for a celebrity, brand or business' so that I can easily access that option. | 2
US-8 | Sprint 2 (2025-12-15 – 2025-12-28) | Branding & Visual Elements | As a user, I want to see Facebook branding, including the logo and tagline so that I recognize the official page. | 2
US-9 | Sprint 2 (2025-12-15 – 2025-12-28) | Accessibility & Responsiveness | As a user, I want the page to be responsive on desktop, tablet, and mobile devices so that I can use it on any device. | 8
US-10 | Sprint 2 (2025-12-15 – 2025-12-28) | Accessibility & Responsiveness | As a user, I want accessibility features like alt text, labels, and tab navigation so that the page is easy to use for everyone. | 8
US-11 | Sprint 2 (2025-12-15 – 2025-12-28) | Performance & Security | As a user, I want the landing page to load in under 2 seconds so that my experience is fast and smooth. | 13
US-12 | Sprint 3 (2025-12-29 – 2025-12-31) | Performance & Security | As a user, I want basic input validation on all forms so that my data is secure from simple errors or threats. | 5
US-13 | Sprint 3 (2025-12-29 – 2025-12-31) | Language Support | As a user, I want to select my preferred language at the bottom of the page so that I can use the site comfortably. | 3