## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-12-01 – 2025-12-14) | User Authentication | As a user, I want to sign up using my email or mobile number so that I can create an account easily. | 5
US-2 | Sprint 1 (2025-12-01 – 2025-12-14) | User Authentication | As a user, I want to log in using my email or phone and password so that I can access my Facebook account. | 5
US-3 | Sprint 1 (2025-12-01 – 2025-12-14) | User Authentication | As a user, I want to use a 'Forgot Password' option so that I can recover my account if I forget my password. | 5
US-4 | Sprint 1 (2025-12-01 – 2025-12-14) | User Authentication | As a user, I want basic input validation during sign up and login so that I reduce errors and protect my data. | 5
US-5 | Sprint 2 (2025-12-15 – 2025-12-28) | User Onboarding & CTAs | As a new user, I want clear call-to-action buttons so that I can easily start the onboarding process. | 2
US-6 | Sprint 2 (2025-12-15 – 2025-12-28) | User Onboarding & CTAs | As a user, I want a prominently displayed 'Create an account' section so that I can quickly find where to register. | 2
US-7 | Sprint 2 (2025-12-15 – 2025-12-28) | Branding and Visual Elements | As a visitor, I want to see Facebook branding including the logo and tagline so that I recognize the platform. | 1
US-8 | Sprint 2 (2025-12-15 – 2025-12-28) | Branding and Visual Elements | As a user, I want a link to create a page for a celebrity, brand or business so that I can explore business-related options. | 3
US-9 | Sprint 2 (2025-12-15 – 2025-12-28) | Accessibility and Language Support | As a user with accessibility needs, I want alt text, labels, and tab navigation so that I can use the landing page effectively. | 8
US-10 | Sprint 2 (2025-12-15 – 2025-12-28) | Accessibility and Language Support | As a user, I want to select my preferred language from options at the bottom of the page so that I can use the page in my language. | 3
US-11 | Sprint 2 (2025-12-15 – 2025-12-28) | Responsive Design and Performance | As a user, I want the landing page to be responsive on desktop, tablet, and mobile so that I can access it on any device. | 8
US-12 | Sprint 3 (2025-12-29 – 2025-12-31) | Responsive Design and Performance | As a user, I want the page to load in under 2 seconds so that I have a fast and smooth experience. | 13