## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-12-01 – 2025-12-14) | User Authentication | As a user, I want to sign up using my email or mobile number so that I can create a new account securely. | 5
US-2 | Sprint 1 (2025-12-01 – 2025-12-14) | User Authentication | As a user, I want to log in using my email or phone along with a password so that I can securely access my account. | 5
US-3 | Sprint 1 (2025-12-01 – 2025-12-14) | User Authentication | As a user, I want a “Forgot Password” recovery process so that I can reset my password if I forget it. | 8
US-4 | Sprint 1 (2025-12-01 – 2025-12-14) | Onboarding and User Engagement | As a new user, I want clear CTA buttons to guide me through onboarding so that I can quickly understand how to use the page. | 3
US-5 | Sprint 1 (2025-12-01 – 2025-12-14) | Onboarding and User Engagement | As a visitor, I want a prominent “Create an account” section so that I am encouraged to register immediately. | 2
US-6 | Sprint 1 (2025-12-01 – 2025-12-14) | Onboarding and User Engagement | As a visitor, I want a link to 'Create Page for a celebrity, brand or business' so that I can create specialized pages if needed. | 3
US-7 | Sprint 2 (2025-12-15 – 2025-12-28) | Branding and Visual Identity | As a user, I want to see the Facebook logo and tagline on the landing page so that I recognize the brand. | 1
US-8 | Sprint 2 (2025-12-15 – 2025-12-28) | Accessibility and Responsiveness | As a user, I want the landing page to be responsive on desktop, tablet, and mobile so that I have a consistent experience across devices. | 8
US-9 | Sprint 2 (2025-12-15 – 2025-12-28) | Accessibility and Responsiveness | As a user with disabilities, I want accessibility features like alt text, labels, and tab navigation so that I can navigate the landing page easily. | 13
US-10 | Sprint 2 (2025-12-15 – 2025-12-28) | Language and Localization | As a user, I want to select my preferred language from options at the bottom of the page so that I can understand the content. | 3
US-11 | Sprint 3 (2025-12-29 – 2025-12-31) | Security and Performance | As a user, I want basic input validation during sign up and login to prevent data breaches and ensure security. | 8
US-12 | Sprint 3 (2025-12-29 – 2025-12-31) | Security and Performance | As a user, I want the landing page to load within 2 seconds so that I have a fast and smooth experience. | 13