## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-12-01 – 2025-12-14) | User Registration & Login | As a user, I want to sign up using my email or mobile number so that I can create an account. | 8
US-2 | Sprint 1 (2025-12-01 – 2025-12-14) | User Registration & Login | As a user, I want a prominently displayed 'Create an account' section so that I can easily find where to register. | 3
US-3 | Sprint 1 (2025-12-01 – 2025-12-14) | User Registration & Login | As a user, I want to log in using my email or phone and password so that I can access my account. | 5
US-4 | Sprint 1 (2025-12-01 – 2025-12-14) | User Registration & Login | As a user, I want to use a 'Forgot Password' recovery process so that I can regain access if I forget my password. | 8
US-5 | Sprint 1 (2025-12-01 – 2025-12-14) | User Onboarding & Engagement | As a new user, I want clear call-to-action buttons so that I can easily proceed through onboarding steps. | 3
US-6 | Sprint 2 (2025-12-15 – 2025-12-28) | User Onboarding & Engagement | As a user interested in creating a business or celebrity page, I want a link to 'Create Page for a celebrity, brand or business' so that I can start that process. | 5
US-7 | Sprint 2 (2025-12-15 – 2025-12-28) | Branding & Language Support | As any user, I want to see Facebook branding, logo, and tagline prominently displayed so that I recognize the brand. | 2
US-8 | Sprint 2 (2025-12-15 – 2025-12-28) | Branding & Language Support | As a user, I want to select my preferred language at the bottom of the page so that I can use the page comfortably. | 3
US-9 | Sprint 2 (2025-12-15 – 2025-12-28) | Responsive Design & Accessibility | As a user, I want the landing page to be responsive on desktop, tablet, and mobile so that I have a good experience on any device. | 13
US-10 | Sprint 2 (2025-12-15 – 2025-12-28) | Responsive Design & Accessibility | As a user with disabilities, I want the page to have alt text, labels, and support tab navigation so that it is accessible. | 13
US-11 | Sprint 3 (2025-12-29 – 2025-12-31) | Performance & Security | As a user, I want the landing page to load in under 2 seconds so that I have a fast and smooth experience. | 8
US-12 | Sprint 3 (2025-12-29 – 2025-12-31) | Performance & Security | As a user, I want basic input validation on forms so that my data is protected from common errors and risks. | 5