## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-12-02 – 2025-12-15) | User Authentication | As a user, I want to sign up using my email or mobile number so that I can create an account. | 5
US-2 | Sprint 1 (2025-12-02 – 2025-12-15) | User Authentication | As a user, I want to log in with my email or phone and password so that I can access my account. | 3
US-3 | Sprint 1 (2025-12-02 – 2025-12-15) | User Authentication | As a user, I want to recover my password using a 'Forgot Password' process so that I can regain access if I forget it. | 8
US-4 | Sprint 1 (2025-12-02 – 2025-12-15) | User Authentication | As a user, I want basic input validation on sign up and login forms so that my data is entered correctly. | 3
US-5 | Sprint 1 (2025-12-02 – 2025-12-15) | Onboarding & User Interaction | As a new user, I want clear call-to-action buttons to guide me through onboarding so that I can start using the service easily. | 3
US-6 | Sprint 2 (2025-12-16 – 2025-12-29) | Branding & Content Display | As a visitor, I want to see Facebook branding including logo and tagline so that I recognize the brand. | 1
US-7 | Sprint 2 (2025-12-16 – 2025-12-29) | Branding & Content Display | As a user, I want a prominent 'Create an account' section so that I can easily find where to register. | 2
US-8 | Sprint 2 (2025-12-16 – 2025-12-29) | Branding & Content Display | As a user, I want a link to 'Create Page for a celebrity, brand or business' so that I can create special pages if needed. | 5
US-9 | Sprint 2 (2025-12-16 – 2025-12-29) | Accessibility & Responsiveness | As a user, I want the landing page to be responsive on desktop, tablet, and mobile so that I have a good experience on any device. | 8
US-10 | Sprint 2 (2025-12-16 – 2025-12-29) | Accessibility & Responsiveness | As a user with accessibility needs, I want alt text, labels, and proper tab navigation so that I can navigate the page easily. | 8
US-11 | Sprint 3 (2025-12-30 – 2025-12-31) | Language & Localization | As a user, I want to select my preferred language from options at the bottom of the page so that I can use the page in my language. | 3
US-12 | Sprint 3 (2025-12-30 – 2025-12-31) | Performance & Security | As a user, I want the landing page to load in under 2 seconds so that I have a fast experience. | 13