## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status
US-1 | Sprint 1 (2025-12-02 – 2025-12-15) | User Registration & Authentication | As a user, I want to sign up using my email so that I can create a new account securely. | 5
US-2 | Sprint 1 (2025-12-02 – 2025-12-15) | User Registration & Authentication | As a user, I want to sign up using my mobile number so that I have flexible options for registration. | 5
US-3 | Sprint 1 (2025-12-02 – 2025-12-15) | User Registration & Authentication | As a user, I want to log in with my email or phone and password so that I can access my account. | 8
US-4 | Sprint 2 (2025-12-16 – 2025-12-29) | User Registration & Authentication | As a user, I want to use a 'Forgot Password' option so that I can recover access if I forget my password. | 5
US-5 | Sprint 2 (2025-12-16 – 2025-12-29) | User Registration & Authentication | As a developer, I want to validate user inputs with basic security checks so that data breaches are minimized. | 8
US-6 | Sprint 2 (2025-12-16 – 2025-12-29) | User Onboarding & Engagement | As a new user, I want clear call-to-action buttons so that I can easily navigate onboarding steps. | 3
US-7 | Sprint 2 (2025-12-16 – 2025-12-29) | User Onboarding & Engagement | As a user, I want the 'Create an account' section prominently displayed so that I can quickly start registration. | 2
US-8 | Sprint 3 (2025-12-30 – 2026-01-12) | Branding & Content Display | As a visitor, I want to see the Facebook logo and tagline so that I recognize the brand immediately. | 1
US-9 | Sprint 3 (2025-12-30 – 2026-01-12) | Branding & Content Display | As a user, I want to find a link to 'Create Page for a celebrity, brand or business' so that I can create a dedicated page easily. | 3
US-10 | Sprint 3 (2025-12-30 – 2026-01-12) | Accessibility & Responsiveness | As a user with disabilities, I want alt text and proper labels on the page so that it is accessible with assistive technologies. | 8
US-11 | Sprint 3 (2025-12-30 – 2026-01-12) | Accessibility & Responsiveness | As a keyboard user, I want to navigate the page using tab keys so that I can interact without a mouse. | 5
US-12 | Sprint 4 (2026-01-13 – 2026-01-26) | Accessibility & Responsiveness | As a user, I want the landing page to be responsive on desktop, tablet, and mobile devices so that I have a good experience on any device. | 13
US-13 | Sprint 4 (2026-01-13 – 2026-01-26) | Performance & Security | As a user, I want the landing page to load within 2 seconds so that I have a fast and smooth experience. | 13
US-14 | Sprint 5 (2026-01-27 – 2026-01-27) | Localization & Language Support | As a user, I want to select my preferred language from options at the bottom of the page so that I can use the page comfortably. | 3