## User Stories
ID | Sprint | Epic | User Story | Story Points (AI) | Priority | Status | Blocker | Suggested Solution
US-1 | Sprint 1 (2025-12-02 – 2025-12-15) | User Authentication | As a user, I want to sign up using my email or mobile number so that I can create a new account. | 5 |  | Done
US-2 | Sprint 1 (2025-12-02 – 2025-12-15) | User Authentication | As a user, I want to see a prominent 'Create an account' section so that I know where to register. | 3 |  | Blocked | Login with mobile number has issues; mobile number validation problem where invalid numbers are treated as valid. | Fix the mobile number validation logic to correctly detect invalid numbers and prevent login attempts with them.
US-3 | Sprint 1 (2025-12-02 – 2025-12-15) | User Authentication | As a returning user, I want to log in using my email or phone and password so that I can access my account. | 5 |  | Done
US-4 | Sprint 2 (2025-12-16 – 2025-12-29) | User Authentication | As a user who forgot my password, I want to use a 'Forgot Password' recovery process so that I can regain access. | 8
US-5 | Sprint 2 (2025-12-16 – 2025-12-29) | New User Onboarding | As a new user, I want clear CTA buttons so that I understand the next steps for onboarding. | 2
US-6 | Sprint 2 (2025-12-16 – 2025-12-29) | Branding and Content Display | As a visitor, I want to see Facebook branding, including the logo and tagline, so that the page feels authentic. | 2
US-7 | Sprint 3 (2025-12-30 – 2026-01-12) | Branding and Content Display | As a user, I want a link to 'Create Page for a celebrity, brand or business' so that I can create pages for my brand if needed. | 3
US-8 | Sprint 3 (2025-12-30 – 2026-01-12) | Language and Accessibility | As a user, I want to select my preferred language at the bottom of the page so that I can use the page comfortably. | 3
US-9 | Sprint 3 (2025-12-30 – 2026-01-12) | Language and Accessibility | As a user with disabilities, I want the page to comply with accessibility standards including alt text, labels, and tab navigation so that I can navigate easily. | 13
US-10 | Sprint 4 (2026-01-13 – 2026-01-26) | Performance and Security | As a user, I want the landing page to load in under 2 seconds so that I have a smooth experience. | 8
US-11 | Sprint 4 (2026-01-13 – 2026-01-26) | Performance and Security | As a user, I want basic input validation checks during sign-up and login to prevent common input errors and improve security. | 5